## ECB Enclosure
| [Project Name] |  |  | P2 Project Number:
Complexity Dimensions | Project Profile & Attributes
| Traditional Project Total Score ~ Under 25 | Moderately Complex Project Total Score 25 - 50 | Highly Complex Project Total Score 51 - 75 | Highly Complex Program / MegaProject Total Score Over 76 | Project Complexity Score |  | 56
Rating Scale | 1 | 2 | 3 | 4 | Attribute Rating Please RATE each dimension (1, 2, 3, or 4) | Weight | If your Project Complexity Score is Above 50, your project may requirement management IAW ECB for Mega Projects. | Project attributes demonstrate characteristics of a TRADITIONAL Project with Moderate Complexity. | Project attributes demonstrate characteristics of a MEGA PROJECT. IAW ECB 2014-20, this project may be added to the list of Mega projects and provided direction for added mgmt.
Project Cost | <$100M | $100M - $299M | $300M - $500M | > $500M | 1 | 1 | 1
Funding | Reimbursable, authorized and appropriated funding, fully funded, one type of funds, one customer providing funds | Cost-shared, authorized and appropriated funding, not fully funded, one or more type of funds, one or more customers providing funds | Cost-shared, reimbursable, questionable authorization and appropriated funding, incrementally funded, several types of funds, several customers providing funds | Cost-shared, reimbursable, program reauthorization and appropriated funding, incrementally funded, several types of funds, several customers providing funds, escalating costs | 2 | 4 | 8
Project/Phase Duration | 1 - 2 years | 2 - 3 years | 3 - 5 years | Multi-year (>5 years) | 3 | 4 | 12
Team Composition and Past Performance | PM: Competent and experienced; Team: Internal, team has history; Team Performance: Good; Contracts: Straightforward; FFP External/Contractor Performance: Good | PM: Competent, little or no experienced; Team: Internal & regional, team has history; Team Performance: Good performance on project delivery; Contracts: Straightforward; FFP External/Contractor Performance: Good | PM: Competent, little or no experience with complex projects; Team: Internal & regional, little or no team history; Performance: Good performance on project delivery; Contracts: Complex; FFP, DB, and other types of construction contracts with greater risk to government. External/Contractor Performance: Unknown and likely to have multiple contractors | PM: Competent, little or no experience with mega projects; must evaluate experience. Team: complex team structure of varying competencies and performance records (e.g. in-house, contractor, virtual, outsourced, etc) Team Performance: Unknown, team has never worked together on project delivery. Contracts: Highly Complex; FFP, DB, and other types of construction contracts with greater risk to government. External/Contractor Performance: Unknown and likely to have multiple contractors | 4 | 2 | 8
Clarity of Problem, Opportunity, Solution | Objectives: Defined and clear; Opportunity/Solution: Easily understood; Scope: Well defined, achievable, and within USACE core competencies Milestones: Traditional methodologies are appropriate; Schedule: Fixed with minimal stakeholder impacts; Budget: Fixed with minimal customer changes | Objectives: Defined but somewhat unclear on methods of delivery; Opportunity/Solution: Partially understood; Scope: Achievable, and within USACE core competencies. Milestones: Traditional methodologies are appropriate with minimal changes/variations; Schedule: Fixed with moderate stakeholder impacts; Budget: Fixed with moderate customer changes | Objectives: Defined, ambiguous; Opportunity/Solution: Ambiguous; Scope: Overly ambitious; similar past projects have required more. Milestones: Traditional methodologies are appropriate; however, stakeholder(s) milestones need to be embedded. Schedule: Fixed schedule; however, some external milestones may drive durations and overall project completion dates. Budget: Fixed; anticipate requesting additional funds for contingency. Anticipate request for additional funding to account for likely unknowns. | Objectives: Defined, increasing ambiguity, methods of delivery are unclear. Opportunity/Solution: Partially understood; Scope: Defined, achievable, and within USACE core competencies Milestones: Traditional methodologies are appropriate; however, many stakeholder(s) milestones need to be embedded. Schedule: Agressive; critical external milestones may adversely impact schedule. Require skilled schedulers. Budget: Fixed; however, we anticipate requesting a major increase in funding due to anticipated customer changes, outdated base costs of original estimate, etc | 1 | 3 | 3
Uniqueness | Project Deliverables: Fully aligned with USACE missions; routine, standard project features | Project Deliverables: Aligned with USACE missions; routine with minor customized project features | Project Deliverables: Aligned with USACE missions; however, there are some customized project features. Presents some technical difficulty. | Project Deliverables: Although aligned with USACE missions; deliverables are complex (i.e. hospital/medical facilities), distinctive and exceptional project features, major technical challenges, etc. | 2 | 2 | 4
Requirements Volatility and Risk | Customer Support: Strong; Requirements: Understood, straight-forward, stable; Functionality: Straightforward | Customer Support: Good; Requirements: Fairly understood; Functionality: Moderately complex | Customer Support: Good; Requirements: Poorly understood by stakeholder groups; Functionality: Highly complex | Customer Support: Varies; Requirements: Fairly understood; however, there are uncertainties based on new regulations; still evolving; Functionality: Many complex "functions of functions" | 3 | 3 | 9
Strategic Importance, Political Implications, Stakeholders | Executive/Congressional Support: Strong; National/International Visibility: Low; Political Implications: None or Low; Communications: Straight-forward; Stakeholder Management: Straight-forward | Executive/Congressional Support: Adequate; National/International Visibility: Moderate; Political Implications: Minor/ moderate; Communications: Challenging; Stakeholder Management: 2-3 stakeholder groups | Executive/Congressional Support: Inadequate; National/International Visibility: High; Political Implications: Major, impacts core mission; Communications: complex; Stakeholder Management: Multiple stakeholder groups with conflicting expectations; visibility at high levels of the organization | Executive/Congressional Support: Unknown or Weak; National/International Visibility: Extremely High; Political Implications: Extremely High, impacts core mission of multiple programs, organizations, states and/or countries; success is critical for competitive or physical survival; Communications: Arduous; Stakeholder Management: Multiple organizations, states and/or countries, regulatory groups, high media attention | 4 | 1 | 4
Level of Change | Organizational Change: Impacts a single business unit, mission, no change in organizational structure, no modifications to USACE standard business practices, USACE IT and automated information systems are adequate Cultural Change: None | Organizational Change: Impacts 2-3 business units/districts, 2-3 missions, no change in organizational structure, no modifications to USACE standard business practices, USACE IT and automated information systems are adequate Cultural Change: May enhance best practices | Organizational Change: Impacts the enterprise, spans functional organizations, or agencies, shifts or transforms many business processes including USACE IT systems Cultural Change: New processes and practices developed | Organizational Change: Impacts multiple organizations, states and/or countries; transformative new venture or discovery Cultural Change: Ground-breaking processes and practices | 1 | 1 | 1
Risk, Dependencies, and External Constraints | Risk Level: Low; Dependencies: One phase project or sequential project phases. External Constraints: No external influences; Integration: No integration issues. | Risk Level: Moderate; Dependencies: No more than two project phases. No more than two prime contractors on construction site. External Constraints: Some external influences; Integration: Challenging integration issues; Potential Damages: Acceptable exposure | Risk Level: High; External Constraints: Key objectives depend on external factors; Integration: Significant integration required; Potential Damages: Significant exposure | Risk Level: Very High; External Constraints: Project success depends largely on multiple external organizations, states and/or countries, regulators; Integration: Unprecedented integration effort; Potential Damages: Unacceptable exposure | 2 | 3 | 6