## BOD Developer
BOD Developer
Instructions: Ensure the listed ranges are reasonable for the project type. If the range is modified, provide rationale for the adjustment. Revise the numbers in blue to reflect project risk and contract duration. Ensure the rationale for the selected value within the range is documented.
| avg | min | max
Base line | 90 | 56.5653 | 269.1139
| Average | Min | Max | Project-Specific Values | Rationale
Contract Duration - The quality or reasonableness of the Gov’t’s contract period of performance. Factors to consider for evaluating schedule quality include: the level of design (DB or DBB), phasing requirements, and aggressive Stakeholder requirements. Was the schedule adequately reviewed prior to award? Does the schedule require significantly higher or lower placement rates than those that have been historically achieved? | 1 | 0.95 | 1.25 | 1.25
Range: 0.95 to 1.25
Design Quality – The quality of the design has a large impact on the project’s outcome. Factors to consider for evaluation of design quality include the number and severity of design review, BCOES and bidder comments, and whether the design was complete and adequately reviewed prior to advertisement. | 1 | 0.95 | 1.25 | 1.15
Range: 0.95 to 1.25
User Requested Changes – Time growth attributed to the stakeholder is typically driven by factors such as the organization’s stability, sensitivity to changing technologies, and extent of follow on contract actions. | 1 | 0.9 | 1.15 | 1.15
Range: 0.90 – 1.15
Contractor Quality – Evaluation of the construction contractor’s method of doing business. Has the contractor successfully completed other, similar projects? | 1 | 0.95 | 1.25 | 1.25
Range: 0.95 – 1.25
Location – The location of the project relative to supply and business centers as well as USACE offices. The remote location of a project may affect the contractor’s ability to procure materials. It may also affect USACE’s ability to manage the project. | 1 | 0.95 | 1.15 | 1.15
Range: 0.95 – 1.15
Differing Site Conditions – Evaluation of the level of risk related to the unknown or mischaracterized aspects of the project site, complexity of foundations, and previous experience working in the geographic area. | 1 | 0.95 | 1.05 | 1.05
Range: 0.95 – 1.05
Weather – The time of year the project is being awarded and the susceptibility of the site to prolonged impacts due adverse weather. | 1 | 0.95 | 1.05 | 1.05
Range: 0.95 – 1.05
Other risk factors such as status of environmental permits/remediation, utility agreements, site access, management staff, joint occupancy, security requirements, special funding, quantity of GA submittals, etc. | 1 | 0.95 | 1.05 | 1.05
Range 0.95 – 1.05
Projected Time Growth | 90 | 56.5653 | 269.1139 | 247.5848
BOD Time Growth Check |  |  |  | Risk-Based BOD | 30% Duration BOD
Project Contract Duration |  |  | 730 | 247.5848 | 219
Day for Day Impacts to Project Schedule Known at BOD Development |  |  | 0 | 247.5848 | 219
BOD Recommendation (cal days from NTP) *ACO/RE to confirm use of maximum between risk-based and 30% duration best represents project risk |  |  | 977.5848
Project NTP date |  |  | 2022-09-15
Original BOD Date |  |  | 2025-05-19 14:02
Formulas:
max = [max, row above]+E32