## SCIF Planning
a | b |  |  | c |  |  | d1 | d2 | e | f | g | h
| Planning Steps | Primary Responsibility for Each Action
| Overall Building needs and ODNI 705 Requirements | Accrediting Official (AO) | Certified TEMPEST Technical Authority (CTTA) | Site Security Manager (SSM) | I-C User / Command / Garrison or Base | Design Agent / USACE | USACE Design Code Status | What does USACE or a Design A/E call it? | Who does this / who provides it? | What is the dependency? | What is the consequence? | Reference
| Requirements Analysis | In table below P= Primary, S= Supporting Role, O= Oversight
1 | A user-defined need for new or remodeled office space is identified |  |  |  | P |  | 0 | Identify basic design criteria, facility size, number of users, etc. Basic SF driven by Standard Designs when available | User-defined needs, initial size may be based on Standards and Criteria in effect | If construciton is the required solution per economic analyses, requirements and applicable criteria will determine project scope and cost. | Failure to clearly identify design requirements for SCIF construction will result in inadequate project scope and cost. There is no guarantee that additional funds would be available, even if reprogramming were possible. The project may be delayed or canceled as a result of missing critical criteria. | AR 420-1.
2 | INTEL tenant defines need for SCIF space as a part of facility requirement |  |  |  | P |  | 0 | INTEL end user provides SCIF Area size requirements | Prepared by the User / SCIF Tenant, coordinated with INTEL (x-2) authority, reviewed and approved by AO. | INTEL authority must validate need for SCIF. | Standards and criteria are the basis for project scope, cost, and design.
2a | Preliminary Site Selection |  |  |  | P |  | 0 | Proposed site is selected by I-C User and coordinated with Garrison or Base | Garrison or Base assesses viable sites on installation; I-C User Command approves site selection. | Can affect project scope, cost, and design based on topological or geographic conditions, building materials and methods, and support facility requirements all affecting overall project scope and cost. | Risk is insufficient scope and cost authorization, delay in BOD if change requires HQDA review and approval; further delays if Congressional authorizaiton is required. | AR 420-1.
2b | One-Time Project Review before Site Acquisition (site selection, purchase, or lease of a building) | S |  |  | P |  | 0 |  | Cognizant Security Authority (CSA) or DoD Component Senior Intelligence Officer (SIO) or their designees shall conduct one-time construction project reviews before site acquisition (purchase or lease of a building). | Coordinate with Land Holding Command (e.g. IMCOM, FORSCOM, Garrison, Base, Landlord). | Without Senior Approvals, the project may fail in mission, leadership or financial support. | DoDM 5105.21, Vol 2, 19 Oct 1012
3 | Identify AO (Accrediting Official) |  |  |  | P |  | 0 |  | Varies but typically Defense Intelligence Agency (DIA) for DoD projects and National Security Agency (NSA) for NSA or NSA-DoD partnered projects. |  | SCIF accreditation. | IC Tech Spec ICD/ICS 705, Ch. 2, A., 1. UFC 4-010-05, Ch. 1.7.
3a | Identify SSM (Site Security Manager) | S |  |  | P |  | 0 |  | Typically named by SCIF end user, may be named by Garrison; reviewed and approved by AO. | Based on the ODNI 705, SSM duties begin with Risk Management Process, immediately after a SCIF is identified to be a part of any project. |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 1. UFC 4-010-05, Ch. 1.7.
4 | Identify CTTA (Certified TEMPEST Technical Authority) | P | S |  |  |  | 0 |  | CTTA notified by AO. |  | SCIF accreditation and identification of TEMPEST countermeasures. | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3., a). UFC 4-010-05, Ch. 1.7.
5 | Technical threat |  | P | S | S |  | 0 |  | AO and SSM coordinate on assessment. | Intelligence Criteria defines the SCIF requirements. | Threat data for the SCIF requirements will influence design. Threat data output will be CLASSIFIED. | IC Tech Spec ICD/ICS 705, Ch. 2, A. UFC 4-010-05, Ch. 1.9.
6 | Physical Threat |  |  | P | S |  | 0 |  | Installation Physical Security Manager or ATO can provide additional local threat information for the assessment. |  | Output will be CLASSIFIED. | OM
7 | Vulnerability Analysis | S |  | P | S |  | 0 | USACE has used the Threat Analysis Information to incorporate AT/FP and other security in prior projects | The Risk Management Baseline is defined in the ODNI 705 Tech Specs Chapter 2. It is completed by SSM and coordinated with the CSA or SIO, then submitted to the AO. | Risk Management Process includes development of blue box tasks at left. | Other threat data may include AT/FP, Blast, or other tactics. Output will be CLASSIFIED. | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3. UFC 4-010-05, Ch. 1.9.
8 | Probability Analysis | S |  | P | S |  | 0 |  | Completed by SSM and coordinated with the IC CSA or Command SIO, then submitted to the AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3. UFC 4-010-05, Ch. 1.9.
9 | Loss/consequence Analysis | S |  | P | S |  | 0 |  | Completed by SSM and coordinated with the IC CSA or Command SIO, then submitted to the AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3. UFC 4-010-05, Ch. 1.9.
10 | Security-in-depth Analysis | S |  | P | S |  | 0 |  | Completed by SSM and coordinated with the IC CSA or Command SIO, then submitted to the AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, B. UFC 4-010-05, Ch. 1.9.2.
11 | DNI TEMPEST Checklist |  | S | P | S |  | 0 |  | DNI TEMPEST checklist is completed by the SSM in coordination with CTTA. | Must have the TSCM identified before design begins, as this will influence adjacent room allocation, wall section design, and other detailing. | Output will be CLASSIFIED. | IC Tech Spec ICD/ICS 705, Ch. 13. UFC 4-010-05, Ch. 1.9.
12 | Compartmented Area Checklist |  |  | P |  |  | 0 |  | Completed by SSM and coordinated with the AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 13.
13 | Security Environment Threat List (SETL) (especially important in OCONUS environment) |  |  | P | S |  | 0 |  | Completed by SSM and coordinated with the AO. |  | Output will be CLASSIFIED. | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3. UFC 4-010-05, Ch. 1.9.1.
14 | Request for Waiver(s) |  |  | S | P |  | 0 |  | User and/or INTEL authority will prepare any necessary waivers, but only the AO may approve. | If the User determines that the ODNI criteria cannot be met, waivers must immediately be implimented, as determinations on waivers can/will impact project scope and cost authorizations or project design. | If the User determines that the ODNI criteria cannot be met, waivers must immediately be implimented, as determinations on waivers can/will impact project scope and cost authorizations or project design. | IC Tech Spec ICD/ICS 705, Ch. 2, A., 2., c. UFC 4-010-05, Ch. 1.7.
Planning Charrette
15 | Review Initial Threat, Physical, Security-in-depth, CTTA approval of CSP | O | S | P | S |  | 0 |  | SCIF Criteria package Developed by SSM, reviewed as needed by CTTA, and coordinated with AO. | Project scope and cost is based on architectural, mechanical, telecommunication, or electrical requirements driven by these documents. | Risk is insufficient scope and cost authorization, delay in BOD if change requires HQDA review and approval; further delays if Congressional authorizaiton is required. | Fiscal Law, MILCON Law, AR 420-1.
16 | Draft Construction Security Plan (CSP) | O |  | P | S |  | 0 | Construction Security Administration is a new requirement, introduced by the ODNI 705 Criteria | SSM, Intel, and User will write the CSP, but it must be reviewed and approved by AO | Identifies who is authorized to work in SCIF space affecting project scope and cost. Project Design is dependant on the CSP as it will influence what rooms are adjacent to the SCIF, what materials are used, how the materials are procured by the contractor, how contrator personnel are cleared, etc. | There is risk in proceeding with the Project before understanding impacts of CSP. CSP can impact design decisions, labor clearance requirements, materials procurement, and construction site security management. | Fiscal Law, MILCON Law, AR 420-1. IC Tech Spec ICD/ICS 705, Ch. 3., B.; Ch. 13. UFC 4-010-05, Ch. 1.12.
17 | Prepare Planning level SCIF cost estimate |  |  |  | P | S | 0 |  | Charrette Cost Estimator (User, Command, or designated agent) should consider using SCIF costing tool or other method to capture big ticket costs of mitigation and SCIF requirements. | Once the SCIF area is identified and the Risk Management Process is completed (blue box tasks at left), IC User or their designated design agent can complete the SCIF costing model for a rough estimate of costs. | SCIF costs are driven by five major factors. These include size/area, risk rating, location (CONUS or OCONUS) and TEMPEST requirements. Projects at this stage should be able to answer these five questions before an esimate is prepared.
| 1) AO = Accrediting Official |  |  |  | 5) CSA = Cognizant Security Authority |  |  |  | Design Code 0 - NO Design Authority (advance information only - PA, Scope, Location
| 2) CTTA = Certified TEMPEST Technical Authority |  |  |  | 6) SIO = Senior Intelligence Officer
| 3) SSM = Site Security Manager |  |  |  | 7) KO = Contracting Officer
4) CSP = Construction Security Plan

## SCIF Design
a | b |  |  | c |  |  | d1 | d2 | e | f | g | h
| Design Steps | Primary Responsibility for Each Action
| Overall Building needs and ODNI 705 Requirements | Accrediting Official (AO) | Certified TEMPEST Technical Authority (CTTA) | Site Security Manager (SSM) | I-C User / Command / Garrison or Base | Design Agent / USACE | USACE Design Code Status | What does USACE or a Design A/E call it? | Who does this / who provides it? | What is the dependency? | What is the consequence? | Reference
| Design Charrette /15% Design, Project Development Report PDR (for Army Only) | In table below P= Primary, S= Supporting Role
1 | Design confirmation to include SCIF in project |  |  | S | S | P | 2 | Design Charette, Design Criteria Development, Project Development Report (PDR for Army Only) | Design Team interprets space planning and room adjacencies with User. | Must confirm all criteria, including Risk Assessment documents, draft CSP guidance, and project cost estimate. | Design Team must properly interpret all SCIF criteria, including construction procedures, to ensure facility success is not compromised due to missing design details or improper construction monitoring.
1b | 10% Design with inclusion of SCIF approved | S |  | P |  | S | 2 |  | Design submitted by SSM or IC User; AO reviews and approves initial SCIF design, issues SCIF number.
1c | SSM confirmed | P |  | S |  |  | 2 |  | AO confirms appointed SSM. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 1. UFC 4-010-05, Ch. 1.7.
1d | Risk Assessment Documents reviewed by AO | P |  |  |  |  | 2 |  | AO issues CSP guidance. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3. UFC 4-010-05, Ch. 1.9.
1e | Draft CSP initialized | S |  | P |  |  | 2 |  | Draft by SSM, reviewed/coordinated with IC User, SIO or CSA, then submitted to AO for review and comment. |  | The majority of the CSP should be marked FOUO. Some portions may require special CLASSIFIED markings above FOUO. Overclassification will make handling of the CSP difficult for daily use, and may restrict pool of bidders. | Fiscal Law, MILCON Law, AR 420-1. IC Tech Spec ICD/ICS 705, Ch. 3., B.; Ch. 13. UFC 4-010-05, Ch. 1.12.
1f | Pre-Design Fixed Facility Checklist (FFC) is completed for first time | S |  | P |  |  | 2 |  | Draft by SSM, sent to AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 13. UFC 4-010-05, Ch. 1.16.2.
1g | TEMPEST Form A is started |  | S | P | S |  | 2 |  | Draft by SSM, sent to CTTA.
1h | Concept Approval Request (CAR) |  |  |  | P |  | 2 |  | Concept Approval is the first critical element in the establishment of a SCIF. Concept approval certifies that a clear operational requirement exists for the SCIF and there is no existing SCIF to support the requirement. | Upon receipt of the request to build a SCIF, the Service CSAs, their designees, or DoD Component SIOs will validate the need for a SCIF and the requirement for the requested level of SCI. The Service CSAs, their designees, or DoD Component SIOs are required to grant concept approval to establish a SCIF, to include contractor SCIFs. They may delegate this approval as deemed necessary. | CSA or SIO holds higher-level I-C visibility and approval of all SCIF projects under their AOR. If any work proceeds before approval of site acquisition or building lease, the SCI Project and Mission may be compromised. | DoDM 5105.21, Vol 2, 19 Oct 1012
1i | PDR and ENG 3086 Estimate (Army Only) |  |  |  |  | P | 2 |  |  |  | Estimate must ensure all design features are captured (e.g. Enhanced Construction, TEMPEST, etc.) | PDR required for Army MILCON only.
35% Design (Concept)
2 | 35% Design Completion |  |  | S |  | P | 2 |  | Design Team develops conceptual floor plans, design analysis calcs & narrative, specifications outline. | Coordinate all security issues with SSM. Changes in design, details, materials, or construction contractor may impact or require changes to the CSP. | Designer must document any changes that effect Scop or Cost as part of the 35% Design Certification Package.
2a | Concept design reviwed by AO, waivers sought as required | P |  | S | S |  | 2 |  | AO reviews and approves concept, including any waivers if needed. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 2., c. UFC 4-010-05, Ch. 1.7.
2b | Risk Assessment Documents finalized | S |  | P | S |  | 2 |  | Risk Assessment Documents finalized by SSM and AO reviews, approves. |  |  | IC Tech Spec ICD/ICS 705, Ch. 2, A., 3. UFC 4-010-05, Ch. 1.9.
2c | Draft CSP finalized, released for review | S |  | P |  | S | 2 |  | Edits by SSM, review/coordinate with designers and approval by AO. |  |  | Fiscal Law, MILCON Law, AR 420-1. IC Tech Spec ICD/ICS 705, Ch. 3., B.; Ch. 13. UFC 4-010-05, Ch. 1.12.
2d | Pre-Design Fixed Facility Checklist (FFC) is finalized | S |  | P |  |  | 2 |  | Edits by SSM, approval by AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 13. UFC 4-010-05, Ch. 1.16.2.
2e | TEMPEST Form A is completed |  | S | P |  |  | 2 |  | Edits by SSM, approved by CTTA.
2f | Budget Estimate Submission |  |  |  | S | P | 2 |  | USACE or Design Agent forwards summary cost estimate, forming basis of 1391 line items to DoD for incorporation into formal DOD Budget Book, and future POM. | SCIF costing in Design is more refined than at Concept. 1391 narratives should capture main SCIF cost driving threats and mitigating measures. | If scope is improperly stated or incomplete, then the SCIF costs risk being vastly understated, resulting in un-accreditable facility, or project delay to seek additional funds.
2g | DD1391 prepared for POM |  |  |  | P | S | 2 | Cost estimate, project summary | Cost Estimate, DD1391, Developed by IC User, Garrison, Base, or their designated agent; the CoS will be consulted when applicable. | DD1391 scope and cost determines when a project will be prioritized above the funding line; establishes all OPA/OMA tail programming and budgeting year; project design and construction execution cannot exceed approved and authorized scope or cost. | Congressional authorization limitations on approved scope cannot be exceeded; cost is limited to 15% above PA and requires HQDA review and approval; project cost in excess of 15% above PA is locked until Congressional approval is received; any scope adjustment and/or cost change (either BTR or ATR) will delay authorization to proceed with modification to original DD1391 scope and cost. | Fiscal Law, MILCON Law, AR 420-1.
60% Design (Development)
3 | Proceed with 60% Design Development |  |  |  |  | P | 6, T |  | Design Team develops preliminary floor plans, updates design analysis, drafts specifications.
3a | CSP monitored and adjusted to fit design and procurement plan | S |  | P |  | S | 6, T |  | Any CSP edits are made by the SSM, coordinated with designers and approved by AO. |  |  | Fiscal Law, MILCON Law, AR 420-1. IC Tech Spec ICD/ICS 705, Ch. 3., B.; Ch. 13. UFC 4-010-05, Ch. 1.12.
3b | Confirm Construction Surveillance Technician (CST) requirements in CSP | S |  | P |  |  | 6, T |  | CSP Edits by SSM, approval by AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 3, A., 4.
3c | Confirm Cleared American Guards (CAG) requirements in CSP | S |  | P |  |  | 6, T |  | CSP Edits by SSM, approval by AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 4, C., 3.
3d | Confirm CSP material purchasing, inspection, shipping, and secure storage area (SSA) requirements | S |  | P |  |  | 6, T |  | CSP Edits by SSM, approval by AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 4.
3e | Confirm CSP SCIF area site access controls for personnel, materials, and vehicles | S |  | P |  |  | 6, T |  | CSP Edits by SSM, approval by AO. |  |  | IC Tech Spec ICD/ICS 705, Ch. 4.
100% Design (Final)
4 | 100% Design Completion, ready to advertise (RTA) |  |  |  |  | P | 6, T | Floor Plans complete, Specifications complete, Current Working Estimate Complete | Design Team completes final floor plans, specifications, design analysis, current working estimate (CWE).
4a | CSP Final attached to Contract Drwgs | S |  | P |  | S | 6, T |  | Any Edits by SSM, approval by AO. | Documents should be releaseable to construction contractor. | Documents should be releaseable to construction contractor. | Fiscal Law, MILCON Law, AR 420-1. IC Tech Spec ICD/ICS 705, Ch. 3., B.; Ch. 13. UFC 4-010-05, Ch. 1.12.
| 1) AO = Accrediting Official |  |  |  | 5) CSA = Cognizant Security Authority |  |  |  | Design Code 2 - Authorized for preparation of Concept Design….will comply with AR 420-1.
| 2) CTTA = Certified TEMPEST Technical Authority |  |  |  | 6) SIO = Senior Intelligence Officer |  |  |  | Design Code 6 - Authorized for final design. Must be developed and approved in accordance with AR 420-1 prior to preparation of final design.
| 3) SSM = Site Security Manager |  |  |  | 7) KO = Contracting Officer |  |  |  | Design Code T - Adapt Build (Army Transformation using Standard Designs from Centers of Standardization)
4) CSP = Construction Security Plan

## SCIF Construction
a | b |  |  | c |  |  | d1 | d2 | e | f | g | h
| Construction Steps | Primary Responsibility for Each Action
| Overall Building needs and ODNI 705 Requirements | Accrediting Official (AO) | Certified TEMPEST Technical Authority (CTTA) | Site Security Manager (SSM) | I-C User / Command / Garrison or Base | Design Agent / USACE | Required: CONUS (C) OCONUS (O) or BOTH (B) | What does USACE or a Design A/E call it? | Who does this / who provides it? | What is the dependency? | What is the consequence? | Reference
| Construction Award and Administration | In table below P= Primary, S= Supporting Role
1 | CSP Final Version Completed and attached to Construction Contract |  |  | P |  | S | B | Design Documents Ready to Advertise (RTA), Contract Award | SSM does final CSP Corrections, AO approves, USACE or Contracting Officer (KO) attaches CSP to construction contract documents. | CSP editing is an iterative process, coordinating decisions about solving risk and threat statements with an ability to document the decisions and execute build. | Failure to solve the threats, mitigate findings during construction, and document the issues into the SCIF records may result in the facility not being accredited, or may impact time and buget to mitigate security issues.
1a | Establish SCIF Project Construction Delivery Team |  |  | S |  | P |  | Coordination | SCIF Stakeholders include the SSM as primary representative of IC end user. Construction Agent/KO/USACE, along with Prime and Subcontractor Construction personnel | Industry best practice to establish communications channels, reinforce roles of security by all stakeholders. Personnel clearance processing, access control and site security training, records collection and management. | Project success depends on good working relations and quick resolution of RFI's or security incidents. Avoid job shutdowns. | Best Practice/Lessons Learned
2 | Construction Documents Security: Follow SSM's Classification Guidance |  |  | S | S | P | B | Classification Guidance | KO should avoid publishing project data on uncleared websites without encryption. Any sensitive Design Data access should be limited to cleared project and contractor personnel.
3 | Initial Construction Site Security |  |  | P | S | S | B | Construction Administration, Site Security, support of Accreditation Process |  | As Required to solve threat and vulnerability analysis, and documented in the CSP instructions |  | DoDM 5105.21, Vol 2, 19 Oct 1012
3a | Establish controlled area boundary and commence access controls of all personnel and materials entering the boundary. |  |  | P | S | S | B |  | SSM coordinate security manpower and response directly with installation security office or alarm response force. | At what point is the boundary of the SCIF 'touched' by the builders? Key points: Grading/Foundations, Floor Slabs, Vertical Construction, Building Envelope Enclosure, Interior Fit-out, insulation, final closure of CAA, Installation of Utilities, Installation of Equipment, including GFE | SCIF accreditation. | IC Tech Spec ICD/ICS 705, Ch. 3 and 7. UFC 4-010-05, Ch. 4.
3b | Establish an access roster of personnel who are cleared to enter the secure work area. All uncleared personnel are kept out or escorted. |  |  | P |  | S | B |  | All Personnel must pass a background investigation and clearance check. Installation Security Office may assist. IC End user may also do separate checks. Contractor must cooperate with personnel records prior to entering secure jobsite. | Construction and design of SCIFs should be performed by US companies using US citizens to reduce risk, but may be performed by US companies using US persons. Mitigations should be implemented when using non-US citizens. Mitigations shall be documented in the CSP. |  | IC Tech Spec ICD/ICS 705, Ch. 3
3c | Provide access roster data to SSM in support of accreditation. |  |  | S |  | P | B | Daily access rosters or electronic records of secure work area access. |  | Small projects may be manually documented. Larger, complex, or long-term projects may dictate electronic recordkeeping. | Supports SCIF accreditation | IC Tech Spec ICD/ICS 705, Ch. 3. UFC 4-010-05, Ch. 4.
3d | Provide for Secure Procurement of Trusted Materials, Secure Shipping and Secure Storage on Jobsite |  |  | P |  |  | O |  | SSM to coordinate all aspects of materials security, and coordinate with CSP instructions. | CSP should dictate HOW to inspect materials: sourcing, visual, manual, x-ray, destructive. CSP should also dictate any Trusted Materials Sourcing issues. |  | IC Tech Spec ICD/ICS 705, Ch. 4.
3e | Inspections of materials, tools, all items brought in to SCIF working boundary. |  |  | P | S |  | B |  |  | CSP should dictate HOW to inspect, and to watch for items from Prohibited Items List |  | IC Tech Spec ICD/ICS 705, Ch. 3. UFC 4-010-05, Ch. 4.
3f | Periodic random inspections of personnel, work areas, and construction in progress. |  |  | P |  |  | B |  | SSM, CST, or designated assignee | CSP and KO should post a list of Restricted and Prohibited items from the Jobsite and Controlled Work Areas. |  | IC Tech Spec ICD/ICS 705, Ch. 3. UFC 4-010-05, Ch. 1.9.
3g | Provide photo and note documentation between major element closures and key details |  |  | P |  |  | B |  | SSM, CST, or designated assignee |  | Photos and notes directly support Accreditation
3h | Inspection and documentation of SCIF perimeter and all supporting utilities |  |  | P |  | S | B |  | Separately from KO administration, the SSM or CST will inspect and document key items in the SCIF Build. | Key items include: Wall assembly before closure and after, acoustical sealing at all edges, uniform paint finish, RF shield install before covering, all SCIF perimeter penetrations, manbars, duct hatches, sound baffles, dielectric couplings, grounding connections, TEMPEST details, PDS. |  | UFC 4-010-05, Ch. 4.
4 | Ongoing Construction Site Security - Continuation of all tasks under part 3 above |  |  | P | S | S | B |  | SSM, CSTs continue documentation of assembly stages, progress, and details. Maintain records of cleared employee entries, visitore, and work areas in progress. |  | Security must also be maintained at any remote storage site, laydown area, or containers that are used to store construction supplies for the interior of the Controlled Area
4a | Documentation of all intermediate phases of construction progress, photos and notes. |  |  | P |  | S | B |  | SSM and CSTs will continue recording progress of intermediate construction details, especially prior to closure or covering major elements (acoustics, RF Shield, manbars in ductwork, etc.) |  |  | UFC 4-010-05, Ch. 4.
4b | If appropriate, reduce the overall security of the controlled construction perimeter. |  |  | P | S | S | B |  | If the Controlled Area does not cover the entire building floor plate, the construction security boundary could be reduced in size as the secure area is enclosed and able to be segregated from the non-secure parts of the bldg. |  | smaller protected areas would be easier to cover with IDS and guard response, as opposed to the entire construction site inside of a fenced perimeter.
4c | Maintain operational control of any interim ACS and IDS that leads into the Controlled Areas. |  |  | P | S | S | B
5 | Informal AO walk-through inspection, punchlist obvious problems prior to government possession and occupancy | P |  | S |  | S | [5 empty] | IC Tech Spec ICD/ICS 705, Ch. 3.
6 | Government takes posession of SCIF Space and moves in |  |  | P
6a | Begin install of GFE. |  |  | P | P | S | O |  | Govt re-programs ACS and IDS after Contractor departure. Govt continues operation of ACS and IDS for all access to the Secure Work Area. | US SECRET Cleared personnel shall perform finish work |  | IC Tech Spec ICD/ICS 705, Ch. 7 (IDS). UFC 4-010-05, Ch. 3.
7 | Other GFE also installed, communications, IT infrastructure, support utilities |  |  | S | P | S | O |  | Govt processes any required compliance testing: ACS, IDS, acoustics, RF Shield performance
7a | AO performs final inspection, lists any issues for correction. | P |  | S |  |  | B |  | Completed by AO and coordinated with the SSM and IC end-user of space. |  | Output will be CLASSIFIED. | IC Tech Spec ICD/ICS 705, Ch. 3. UFC 4-010-05, Ch. 4.
7b | After final approval, AO issues certificate of occupancy for SCIF mission inside new accredited space. | P |  | S | [7 empty] | IC Tech Spec ICD/ICS 705, Ch. 1. UFC 4-010-05, Ch. 4.
8 | SSM forwards final copies of all IC forms and records to AO for final records adminstration. | S |  | P | [7 empty] | IC Tech Spec ICD/ICS 705, Ch. 1.
9 | Collect and share Lessons Learned from SCIF Project from SSM, IC User, and stakeholders | [7 empty] | USACE PM, KO, and others |  | constant product and process improvement, sharing of best practices and lessons learned see link at https://apps.usace.army.mil/sites/MMLL/sitepages/home.aspx | Military Programs Lessons Learned - Home (army.mil)
| 1) AO = Accrediting Official |  |  |  | 5) CSA = Cognizant Security Authority
| 2) CTTA = Certified TEMPEST Technical Authority |  |  |  | 6) SIO = Senior Intelligence Officer
| 3) SSM = Site Security Manager |  |  |  | 7) KO = Contracting Officer
4) CSP = Construction Security Plan