# Sample Engineering Quality Management Content in PMP

This document provides guidance regarding Engineering contribution to the quality management content in the Project Management Plan (PMP), as outlined in the Project Delivery Business Process (PDBP) in Engineering Manual (EM) 5-1-11. In addition, content contributions by other branches (PPMD, Construction, Contracting, etc.) shall be merged by the Project Manager (PM) in the PMP in order to avoid redundancies.

Each section consists of two parts:

BACKGROUND: Provides recommendations to draft the section effectively and efficiently.

EXAMPLE: Illustrates how each section may look in a drafted PMP. The examples do not come from a single PMP and range in program, size and complexity. They should not be construed as the minimum requirements of a PMP – that can only be determined depending on the project-specific circumstances.

# TEAM ESTABLISHMENT (PROC2020)

- Project Delivery Team (PDT)

BACKGROUND: The PDT is involved with the day-today production of a product/project, and mostly includes designers (Architect-Engineer or In-House).

EXAMPLE:

| PROJECT DELIVERY TEAM (PDT) |  |  |  |  |
| --- | --- | --- | --- | --- |
| NAME | ROLE | PHONE | EMAIL | RESPONSIBILITIES |
|  | Project Manager |  |  |  |
|  | Technical Lead |  |  |  |
|  | Civil Designer |  |  |  |
|  | Structural Designer |  |  |  |
|  | Architect Designer |  |  |  |
|  | Interior Designer |  |  |  |
|  | Landscape Architect Designer |  |  |  |
|  | Fire Protection Designer |  |  |  |
|  | Mechanical Designer |  |  |  |
|  | Electrical Designer |  |  |  |
|  | Telecommunications Designer |  |  |  |
|  | Cost Estimator |  |  |  |
|  | Sustainability Manager |  |  |  |
|  | CADD/BIM Manager |  |  |  |

- Design Quality Control (DQC) Review Team

BACKGROUND: The DQC Review Team includes USACE Home District reviewers that are not involved with the day-to-day production of a product/project.

EXAMPLE:

| DESIGN QUALITY CONTROL (DQC) REVIEW TEAM |  |  |  |  |
| --- | --- | --- | --- | --- |
| NAME | ROLE | PHONE | EMAIL | RESPONSIBILITIES |
|  | Review Lead |  |  |  |
|  | Contracting Officer Representative |  |  |  |
|  | Civil Reviewer |  |  |  |
|  | Structural Reviewer |  |  |  |
|  | Architecture Reviewer |  |  |  |
|  | Interior Design Reviewer |  |  |  |
|  | Landscape Architect Reviewer |  |  |  |
|  | Fire Protection Reviewer |  |  |  |
|  | Mechanical Reviewer |  |  |  |
|  | Electrical Reviewer |  |  |  |
|  | Telecommunications Reviewer |  |  |  |
|  | CAD/BIM Reviewer |  |  |  |
|  | Sustainability Reviewer |  |  |  |
|  | Specifications Reviewer |  |  |  |

- Independent Technical Review (ITR) Team

BACKGROUND: The ITR Team includes stakeholders and specialists/experts from another district or center that are not involved with the day-today production of a product/project.

EXAMPLE:

| INDEPENDENT TECHNICAL REVIEW (ITR) TEAM |  |  |  |  |
| --- | --- | --- | --- | --- |
| NAME | ROLE | PHONE | EMAIL | RESPONSIBILITIES |
|  | Regional Technical Specials |  |  |  |
|  | Subject Matter Expert |  |  |  |
|  | Center of Expertise |  |  |  |
|  | Civil Reviewer [XXX] District |  |  |  |
|  | Structural Reviewer [XXX] District |  |  |  |
|  | Architecture Reviewer [XXX] District |  |  |  |
|  | Interior Design Reviewer [XXX] District |  |  |  |
|  | Landscape Architect Reviewer [XXX] District |  |  |  |
|  | Fire Protection Reviewer [XXX] District |  |  |  |
|  | Mechanical Reviewer [XXX] District |  |  |  |
|  | Electrical Reviewer [XXX] District |  |  |  |
|  | Telecommunications Reviewer [XXX] District |  |  |  |
|  | CAD/BIM Reviewer [XXX] District |  |  |  |
|  | Sustainability Reviewer [XXX] District |  |  |  |
|  | Specifications Reviewer [XXX] District |  |  |  |
|  | Stakeholder #1 |  |  |  |
|  | Stakeholder #2 |  |  |  |

# ACTIVITY, SCHEDULE DEVELOPMENT, AND MAINTENANCE (PROC2030)

- Schedule of Reviews

BACKGROUND: The schedule of reviews provides a general overview of QC and QA activities, and is integrated by the PM into the overall project schedule.  This schedule also documents reviews that have been completed to the satisfaction of the TL.

EXAMPLE:

| SCHEDULE OF REVIEW |  |  |  |
| --- | --- | --- | --- |
| MILESTONE | START DATE | FINISH DATE | DURATION (CALENDAR DAYS) |
| Charrette Report |  |  |  |
| Charrette Report Review |  |  |  |
| Concept (35%) Design Submittal |  |  |  |
| Concept (35%) Design DQC Review |  |  |  |
| Concept (35%) Design ITR and BCOES Review |  |  |  |
| Finalize VE Report |  |  |  |
| Interim (65%) Design Submittal |  |  |  |
| Interim (65%) Design DQC Review |  |  |  |
| Interim (65%) Design ITR |  |  |  |
| Final (95%) Design Submittal |  |  |  |
| Final (95%) Design DQC Review |  |  |  |
| Final (95%) Design ITR |  |  |  |
| Final (95%) BCOES Review |  |  |  |
| Final Backcheck (100%) Design |  |  |  |
| Final Backcheck (100%) DQC Review and ITR Closeout and Certification |  |  |  |
| BCOES Certification |  |  |  |

# RESOURCE ESTIMATE DEVELOPMENT (PROC2040)

- Budget

BACKGROUND: The budget should be broken down into the different types of reviews.

EXAMPLE:

| PROGRAM AMOUNT (PA): [XXX] |  |
| --- | --- |
| ACTIVITY | BUDGET |
| District Quality Control (DQC) |  |
| Independent Technical Review (ITR) |  |
| Biddability, Constructability, Operability, Environmental, and Sustainability (BCOES) |  |
| Quality Assurance (QA) |  |
| Value Engineering Study |  |
| Total: |  |

# CRITICAL ASSUMPTIONS AND CONSTRAINTS (REF8005G)

- Codes and Criteria

BACKGROUND: List applicable Codes and criteria mandated.

EXAMPLE:

| CODES AND CRITERIA |  |
| --- | --- |
| NUMBER | NAME |
|  | Higher Authority Mandates |
| UFC 1-200-01 | General Building Requirements |
| NFPA 101 | Life Safety Code |
| IBC 2024 | International Building Code |
| STAKEHOLDER CRITERIA |  |
| U.S. Air Force Regulations and Instructions |  |
| U.S. Air Force Information Systems |  |
| Installation Design Guidance |  |
| Public Laws |  |
| Executive Orders |  |
| National Security Telecommunications and Information Systems Security Committee |  |
| U.S. Army Regulations |  |
| VA Design Guide |  |
| U.S. Army Information Systems Command |  |

- Unique design factors and complexity of project

BACKGROUND: List unique features of design requiring special review attention.

EXAMPLE:

| PROJECT SPECIFIC DESIGN FEATURES / COMPLEXITY |  |
| --- | --- |
| SCIF | Review of SCIF facilities should be performed by SME. |
| Mission critical | Facility is mission critical and has unique features to maintain operation. |
| Ballistic protection | This project includes ballistic resistance glazing and walls for the waiting room. Project shall be reviewed in accordance with UL 752. |

- RISK MANAGEMENT PLAN (REF8007G)

- Risk/hazard factors

BACKGROUND: List potential risks to the project, what would trigger the risk and the potential impact of that risk. This section is meant to analyze potential setbacks up front to address those issues early and mitigate potential problems.  Information provided here will contribute to the PMP’s risk register.

EXAMPLE:

| RISK / HAZARD FACTORS |  |  |  |
| --- | --- | --- | --- |
| TYPE OF RISK | RISK DESCRIPTION | TRIGGERS | POTENTIAL IMPACT |
| Schedule | Failure to meet a milestone | Scope change | Schedule Delay |
| Schedule | Remove 65% design submittal requirement | Compress project schedule | Decrease in design quality |
| Complexity | MEDIUM: Technically specific design criteria on SCIF | More time and detail required | Need a technical expert to assist with design (time & money) |
| Resource availability | Limited electrical engineering resources are available | Electrical Engineer priorities shift | Schedule Delay |

- QUALITY MANAGEMENT PLAN(REF8008G)

- QUALITY CONTROL PROCESS

BACKGROUND: Outline the project-specific quality control process here.  This can be achieved by either referencing the district’s Business Quality Process or noting the process here. Typical documentation is in paragraph form and describes the process and when it takes place.  Adapt project-specific processes, if necessary, to achieve quality.

EXAMPLE:

Reference [X] District Business Quality Process #### “Product Development In-House” for specific quality control activities.

-OR-

DQC review: DQC reviews will take place at each milestone. A discipline specific reviewer, separate to the day-to-day production, will review the product at a detailed level.  When necessary, the reviewer and designer will problem-solve together to develop the best design solutions.  Each discipline shall have a checklist of items to review and check off before a product goes out for review.

The Branch chief will check any deliverables before review for quality control measures and consistency and has the ability to hold up any product they do not see meets the level of quality required.

- QUALITY ASSURANCE PROCESS

BACKGROUND: Outline the project-specific quality assurance process here.  This can be achieved by either referencing the district’s Business Quality Process or noting the process here.  Typical documentation is in paragraph form, and describes the process and when it takes place.  Adapt project-specific processes, if necessary, to achieve quality.

EXAMPLE:

Reference [X] District Business Quality Process #### “Contract Design for Quality” for specific quality assurance activities.

-OR-

Quality Assurance:  The TL will ensure that the processes as identified in this PMP and ER 1110-3-12 are being properly implemented, including but not limited to:

- Verification of PDT and ITR team are the same technically-qualified staff as identified in this PMP.

- Assurance that all engineering and design review comments have been adequately resolved in future submittals.

- Verification that the latest version of the construction documents is used in the solicitation package.

- The COR will ensure that the A-E is meeting the submittal, schedule, and quality requirements of the A-E services contract.