## ReviewChklist
SAMPLE CHECKLIST FOR COST ESTIMATE PREPARATION OR REVIEWER CHECKLIST
Y | N | ITEM
1. Comply with applicable cost engineering guidance, e.g., ER 1110-1-1300 and ER 1110-3-1300 for Army projects. For Navy guidance refer to FC 1-300-09N. For Air Force guidance contact AFCEC/CO.
2. Prepare cost estimate using agency approved estimating software, as appropriate, and structured using the appropriate Uniformat II for military programs.
3. Prepare Basis of Estimate with statement summarizing purpose of cost estimate and brief statement and description of the project.
4. Identify stage of cost estimate (i.e. planning estimates, and IGE).
5. Clearly identify and define assumptions, identify significant features upon which the cost estimate is based.
6. Identify significant risks the impact cost and schedule during preparation of the estimate.
7. Develop notes throughout the cost estimate, particularly to identify sequencing of construction activities and crew productions.
8. Separate subcontract work from prime contract work.
9. Identify separate markups for subcontractors and prime contractor.
10. Identify sources of unit prices and vendor or subcontractor quotes.
11. Include design contingencies and construction contingencies in the cost estimate, if appropriate.
12. Include cost growth (escalation) from the date of the cost estimate to the mid-point of construction and/or operation. Identify source of index used for escalation, e.g., (UFC 3-701-01, Engineering News Record, Turner Construction Index, etc.).
13. Determine if cost estimate is within budget.
14. Minimize use of lump sum pricing. If used, the lump sum description must indicate in detail what is included in the price and whether or not it is based on a quotation.
15. Use prevailing current location-specific wage rates in the cost estimate. Consider market rates for labor to ensure there is reasonable competition on-going in the area where the construction is being performed and/or may be competing with the domestic projects being constructed.
16. Check derived unit costs with historical data when available. Override Cost Book labor and/or material unit prices as required, to fit project-specific conditions.
17. Complex or major features of a project should include a detailed breakdown for labor, equipment and material.
18. Job Office Overhead should be calculated beforehand if a percentage is used, to verify (i.e., development of a construction schedule) that an adequate percentage is used.
19. Calculate home office overhead as a percentage of total contract cost.
20. Include bond costs in cost estimate.
21. Calculate prime and subcontractor profit by Weighted Guidelines method.
22. Provide Cost Engineer point of contact and telephone number.
23. Include all applicable costs for permits, licenses, taxes, and fees.