## CE-1
CONSTRUCTION ESTIMATE |  |  |  | SHEET 1 OF 1
PROJECT | CONSTRUCTION PUMP PLANT A |  |  | SOLICITATION NO.
DACW97-01-0001
ITEM NO. | DESCRIPTION | ESTIMATED QUANTITY | UNIT | UNIT PRICE | ESTIMATED AMOUNT
1 | PUMPING PLANT A | 1 | JOB | L.S. | 913500
|  |  | Total |  | 913500
Approved:
CHIEF, COST ENGINEERING SECTION
Date
CONSTRUCTION ESTIMATE | JAN 2008

## CE-2
CONSTRUCTION ESTIMATE DETAIL SUMMARY SHEET | [13 empty] | SHEET 1 OF X
PROJECT: | PUMP PLANT A
BID ITEM |  |  |  | EQUIPMENT | MOBILIZATION AND DEMOBILIZATION | LABOR | MATERIALS | SUPPLIES | SUBTOTAL | DISTRIBUTED COST | TOTAL COST | UNIT COSTS | ADJUSTED
NO | DESIGNATION | Qty | UNIT | [6 empty] | 40.54% |  |  | UNIT COSTS | AMOUNT | NO
1 | PUMP PLANT A | 1 | JOB | 109436 |  | 150001 | 408385 | 24219 | 692041 | 280563.802 | 972604.802 | L.S. | L.S. | 972604.802
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
TOTALS |  |  |  | 109436 | 0 | 150001 | 408385 | 24219 | 692041 | 280563.802 | 972604.802 |  |  | 972604.802
JAN | 2008

## CE-3
CONSTRUCTION ESTIMATE WORKSHEET SUMMARY | [5 empty] | SHEET 1 OF X
PROJECT:
CONSTRUCT PUMP PLANT A
SUBJECT: | [5 empty] | QUANTITY
PUMP PLANT A | [5 empty] | 1-JOB
SUBITEM |  | EQUIPMENT | LABOR | MATERIALS | SUPPLIES | SUBTOTAL | REF. PG.
CARE & DIVERSION OF WATER |  | 35200 | 7800 | 900 | 1000 | 44900 | 4
EARTHWORK FOR STRUCTURE |  | 45100 | 6200 | 0 | 490 | 51790 | 7
SUBSTRUCTURE |  | 3806 | 51581 | 26785 | 12809 | 94981 | 11
MACHINERY & APPT. |  | 12800 | 28300 | 265000 | 4320 | 310420 | 18
GATE & VALVES |  | 2200 | 12400 | 38100 | 400 | 53100 | 22
AUXILIARY EQUIPMENT |  | 500 | 1200 | 8400 | 100 | 10200 | 24
ASSOCIATES ITEMS |  | 1200 | 3650 | 4100 | 0 | 8950 | 26
TOTAL |  | 100806 | 111131 | 343285 | 19119 | 574341
JAN | 2008

## CE-4
CONSTRUCTION ESTIMATE WORKSHEET |  |  | SHEET 1 OF 2
PROJECT:
CONSTRUCT PUMP PLANT A
SUBJECT: |  | QUANTITY
SUBSTRUCTURE |  | 165 M3
|  | SHIFTS PER DAY | HOURS PER SHIFT
|  | 1 | 10
PLAN OF OPERATIONS
USE READY-MIX SUPPLIERS FOR 20.7 MPA CONCRETE
1 | PLACE CONCRETE - 164M3 @ 7.5M3/HR = SAY 22 HRS
USE: HYD S. P. CRANE - 30TC 7522000
CONCRETE BUCKET - 2 CY B30Z1055
AIR COMPRESSOR - 250CFM A15Z0140
CONCRETE VIB - 2.5 IN AIR C65XX001
LABOR FOREMAN
5 LABORERS
1 CARPENTER
2 | FINISH WORK
FLOAT2 CEMENT FIN - 293M2/16.3M2/HR = SAY 18 HRS
STEEL TROWEL - 109M2/7.3M2/HR = SAY 15 HRS
USE I CEMENT FIN
1 EA. POWER TROWEL
3 | INSTALL WATER STOP - 8"
1 CARP @ 2MIHR = 5312 = SAY 27 MHRS
4 | CURE CONCRETE -
USE 2 LABORERS - 4 HR/DAY X 14 DAYS = 56 HOURS
JAN | 2008
CONSTRUCTION ESTIMATE WORKSHEET |  |  | SHEET 2 OF 2
PROJECT:
CONSTRUCT PUMP PLANT A
SUBJECT: |  | QUANTITY
SUBSTRUCTURE |  | 165 M3
|  | SHIFTS PER DAY | HOURS PER SHIFT
|  | 1 | 10
PLAN OF OPERATIONS
5 | USE SUBCONTRACT QUOTE FROM RESTEEL 7.4MT
6 | FORMING - USE 1 CARP 4/M + 4 CARP
A: BLDG WALL FORMS - 2 USES - 315M2/2 = 158M2
Bldg @ 3.9M2/CREW HR = 40.5 CREW HRS
B: SET & STRIP
WALLS @ 3.9M2/CREW HRS - 314M2/3.9 = 80.5 HRS
SLAB EDGE @ 7M2/CREW HRS 53/7 = 7.6 HRS
ELEVATOR SLAB @ 3M2/CREW HRS = 109/3 = 36.3 HRS
SET/REMOVE SHORING @ 2M2/HR = 109/2 = 54.5 HOURS
TOTAL CREW HRS, BLDG/SET/STRIP = 219.4
SAY 220 HRS
C: FORM LUMBER -
SLAB @ 30BF/M2 = 30(53) = 1590 BF
WALL @ 358F/M2 = 35 (153) = 5530 BF
ELEV SLAB @ 40BF/M2 = (109) = 4360 BF
TOTAL 11480 BF
JAN | 2008

## CE-5
CONSTRUCTION ESTIMATE DETAIL WORKSHEET A | [6 empty] | SHEET X OF XX | CONSTRUCTION ESTIMATE DETAIL WORKSHEET C | [7 empty] | SHEET X OF XX
SUBJECT: | [6 empty] | QUANTITY | SUBJECT: | [7 empty] | QUANTITY
SUBSTRUCTURE CONCRETE | [6 empty] | 165 M3 | SUBSTRUCTURE CONCRETE | [7 empty] | 165 M3
EQUIPMENT | [7 empty] | EQUIPMENT
UNIT OF EQUIPMENT |  |  | SIZE | NO. | HOURS* | RATE | AMOUNT | UNIT OF EQUIPMENT |  |  |  | SIZE | NO. | HOURS* | RATE | AMOUNT
1. PLACE CONCRETE | [7 empty] | AIR HOSE - 100LF - A20Z0430 |  |  |  | 1.5" | 1 | 22 | 42.81 | 941.82
HYD S.P.R.T. CRANE - C75Z2000 |  |  | 30T | 1 | 22 | 42.61 | 937.42 | HYD S.P.R.T. CRANE - C75Z2000 |  |  |  | 30T | 1 | 22 | 0.56 | 12.32
CONCRETE BUCKET - B30Z1055 |  |  | 2CY | 1 | 22 | 0.56 | 12.32 | CONCRETE BUCKET - B30Z1055 |  |  |  | 2CY | 1 | 22 | 8.66 | 190.52
AIR COMPRESSOR - A15Z0140 |  |  | 250CFM | 1 | 22 | 8.66 | 190.52 | AIR COMPRESSOR - A15Z0140 |  |  |  | 250CFM | 2 | 22 | 0.85 | 37.4
CONCRETE VIBRATOR - C65XX001 |  |  | 2.5" | 2 | 22 | 0.85 | 37.4 | CONCRETE VIBRATOR - C65XX001 |  |  |  | 2.5" | 2 | 22 | 0.56 | 24.64
AIR HOSE - 100LF - A20Z0430 |  |  | 1.5" | 2 | 22 | 0.56 | 24.64 | STEEL POWER TROWEL - C25Z1560 |  |  |  | 46" | 1 | 15 | 1.63 | 24.45
[8 empty] | (*NOTE: USE WORKING HOURS) |  |  |  | SUBTOTAL |  |  |  | 1231.15
2. FINISH CONCRETE | [11 empty] | MOBILIZATION AND DEMOBILIZATION
STEEL POWER TROWEL - C25Z1560 |  |  | 46" | 1 | 15 | 1.63 | 24.45 |  |  |  |  | SMALL TOOLS | 5% | OF LABOR |  | 2539.7245
[12 empty] | TOTAL EQUIPMENT COST |  |  |  | 3770.8745
EQUIPMENT RATES TAKEN FROM EP-1110-1-8 | [7 empty] | LABOR | OPERATIONS |  | CRAFT |  | NO. | HOURS | RATE | AMOUNT
VOL #8, AUG 95. RATES HAVE BEEN ADJUSTED FOR | [8 empty] | 1. PLACE CONCRETE |  | FOREMAN X-LABOR |  | 1 | 22 | 32.56 | 716.32
50 HR WORK WEEK. | [10 empty] | X-LABOR |  | 5 | 22 | 29.51 | 3246.1
*NOTE: USE WORKING HOURS |  |  | SUBTOTAL |  |  |  | 1226.75 |  |  |  | X-EQOPRMED |  | 1 | 22 | 38.15 | 839.3
|  |  | SMALL TOOLS | 2% | OF LABOR |  | 1031.6242 |  | 2. FINISH CONCRETE |  | X-CEMTFINR |  | 1 | 51 | 33.63 | 1715.13
|  |  | TOTAL EQUIPMENT COST |  |  |  | 2258.3742 |  | 3. INSTALL WATER STOP |  | X-CARPENTER |  | 1 | 27 | 35.76 | 965.52
LABOR | [8 empty] | 4. CURE CONCRETE |  | X-LABOR |  | 2 | 56 | 29.51 | 3305.12
OPERATIONS |  | CRAFT |  | NO. | HOURS | RATE | AMOUNT |  | 5. FORMWORK |  | FOREMAN X-CARPENTER |  | 1 | 220 | 38.81 | 8538.2
1. PLACE CONCRETE |  | FOREMAN X-LABOR |  | 1 | 22 | 32.56 | 716.32 |  |  |  | X-CARPENTER |  | 4 | 220 | 35.76 | 31468.8
|  | X-LABOR |  | 5 | 22 | 29.51 | 3246.1 |  | TOTAL LABOR COSTS | [6 empty] | 50794.49
|  | X-CARPENTER |  | 1 | 22 | 35.76 | 786.72 | MATERIALS | DESCRIPTION |  |  | UNIT | QUANTITY |  | PRICE | AMOUNT
|  | X-EQOPRMED |  | 1 | 22 | 38.15 | 839.3 |  | *READY MIX CONCRETE - 20.7 MPA |  |  | M3 | 175 |  | 78.6 | 13755
[9 empty] | *WATER STOP 9 PVC X 3/8" THK |  |  | M | 53 |  | 11.75 | 622.75
2. FINISH CONCRETE | [8 empty] | SUBTOTAL: | 14377.75
FLOAT |  | X-CEMTFINR |  | 2 | 18 | 33.63 | 1210.68 |  | SALES TAX: | 6% |  |  |  |  | 6% | 862.665
STEEL TROWELL |  | X-CEMTFINR |  | 1 | 15 | 33.63 | 504.45 |  | *RESTEEL SUBCONTRACTOR |  |  | MT | 7.4 |  | 1560 | 11544
[9 empty] | TOTAL MATERIALS COST | [6 empty] | 26784.415
3. INSTALL WATER STOP |  | X-CARPENTER |  | 1 | 27 | 35.76 | 965.52 | SUPPLIES | DESCRIPTION |  |  | UNIT | QUANTITY |  | PRICE | AMOUNT
[9 empty] | CURING FORM TIES & OIL |  |  | M2 | 476 |  | 10.07 | 4793.32
4. CURE CONCRETE |  | X-LABOR |  | 2 | 56 | 29.51 | 3305.12 |  | FORM PLYWOOD 1/2" |  |  | M2 | 56 |  | 7.42 | 415.52
[9 empty] | FORM PLYWOOD 3/4" |  |  | M2 | 267 |  | 10.6 | 2830.2
5. FORMWORK |  | FOREMAN X-CARPENTER |  | 1 | 220 | 38.81 | 8538.2 |  | FORM LUMBER |  |  | MBF | 12 |  | 397.5 | 4770
|  | X-CARPENTER |  | 4 | 220 | 35.76 | 31468.8 |  | TOTAL SUPPLIES COST | [6 empty] | 12809.04
TOTAL LABOR COSTS | [6 empty] | 51581.21 | TOTAL | [7 empty] | 90387.945
JAN | 2008 | [6 empty] | REMARKS: (Indicate by asterisk (*) prices on items which are based on quotation from manufacturers or suppliers) |  |  |  |  | DATE |  |  | PREPARED BY
[13 empty] | 2010-03-01 |  |  | J. SMITH
CHECKED BY
J. DOE
[8 empty] | JAN | 2008
CONSTRUCTION ESTIMATE DETAIL WORKSHEET B | [6 empty] | SHEET X OF XX
SUBJECT: | [5 empty] | QUANTITY
SUBSTRUCTURE CONCRETE | [5 empty] | 165 M3
MATERIALS
DESCRIPTION |  |  | UNIT | QUANTITY |  | PRICE | AMOUNT
* READY MIX CONCRETE 20.7 MPA (INCLUDES WASTE) |  |  | M3 | 175 |  | 78.6 | 13755
* WATER STOP 9 PVC X 3/8" THK |  |  | M | 53 |  | 11.75 | 622.75
SUBTOTAL : |  | 14377.75
SALES TAX: |  | 6% |  |  |  | 6% | 862.665
RESTEEL SUBCONTRACTOR |  |  | MT | 7.4 |  | 1560 | 11544
TOTAL MATERIALS COST | [6 empty] | 26784.415
SUPPLIES
DESCRIPTION |  |  | UNIT | QUANTITY |  | PRICE | AMOUNT
CURING SUPPLIES |  |  | M2 | 476 |  | 0.5 | 238
FORM PLYWOOD 1/2" |  |  | M2 | 56 |  | 7 | 392
FORM PLYWOOD 3/4" |  |  | M2 | 267 |  | 10 | 2670
FORM LUMBER |  |  | MBF | 12 |  | 375 | 4500
FORM TIES & OIL |  |  | M2 | 476 |  | 9 | 4284
[6 empty] | SUBTOTAL: | 12084
SALES TAX: |  | 6% | x | 12084 |  |  | 725.04
TOTAL SUPPLIES COST | [6 empty] | 12809.04
EQUIPMENT | [6 empty] | 2258.3742
LABOR | [6 empty] | 51581.21
MATERIALS | [6 empty] | 26784.415
SUPPLIES | [6 empty] | 12809.04
TOTAL | [6 empty] | 93433.0392
REMARKS: (Indicate by asterisk (*) prices on items which are based on quotation from manufacturers or suppliers) | [5 empty] | DATE | PREPARED BY
[6 empty] | 2010-03-01 | J. SMITH
CHECKED BY
J. DOE
JAN | 2008

## CE-6
ESTIMATE DETAIL SUMMARY SHEET
PROJECT: | WAREHOUSE BUILDING |  |  | ESTIMATOR | J. SMITH |  |  |  | SHEET 1 OF 1
LOCATION: | FORT HUNTSVILLE, AL |  |  | CHECKED BY | J. DOE |  |  |  | DATE PREPARED |  |  | 2008-01-30
BID ITEM |  |  |  | SUB CONTRACT COST | PRIME CONTRACT COST | TOTAL DIRECT COST | OVERHEAD | SUB-TOTAL | PROFIT | SUB-TOTAL | BOND | TOTAL COST
No. | Description | Quantity | Unit Meas |  |  |  | 19.5% |  | 7.05% |  | 1%
1 | WAREHOUSE BUILDING | JOB | L.S. | 335781 | 619361 | 955142 | 186252.69 | 1141394.69 | 80468.3256 | 1221863.0156 | 12218.6302 | 1234081.6458
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SITEWORK | JOB | L.S. |  | 294636 | 294636 | 57454.02 | 352090.02 | 24822.3464 | 376912.3664 | 3769.1237 | 380681.4901
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 335781 | 913997 | 1249778 | 243706.71 | 1493484.71 | 105290.6721 | 1598775.3821 | 15987.7538 | 1614763.1359
JAN | 2008

## CE-7
COST ESTIMATE ANALYSIS |  |  | INVITATION/CONTRACT NO. | [5 empty] | EFFECTIVE PRICING DATE |  |  |  | DATE PREPARED
|  |  | DACA85-8-97-8-0001 | [5 empty] | 1997-08-01 |  |  |  | 1997-05-10
PROJECT: |  |  | CODE (Check one) | [5 empty] | DRAWING NO. |  |  |  | SHEET 1 OF 1 SHEETS
WAREHOUSE BUILDING | [8 empty] | 1
LOCATION: | [8 empty] | ESTIMATOR |  |  |  | CHECKED BY
FORT HUNTSVILLE, AL | [8 empty] | J. SMITH |  |  |  | J.DOE
TASK DESCRIPTION |  | QUANTITY |  | LABOR |  |  |  | EQUIPMENT |  | MATERIAL |  | TOTAL |  | SHIPPING
|  | NO. OF UNITS | UNIT MEAS | MH UNIT | TOTAL HRS | UNIT PRICE | COST | UNIT PRICE | COST | UNIT PRICE | COST |  |  | UNIT WT | TOTAL WT
01 SUBSTRUCTURE 01 STANDARD FDN
| WALL FTG FORMS | 52 | M2 | 0.75 | 39 | 23.34 | 1213.68 | 0.43 | 22.36 | 6.67 | 346.84 | 1582.88 |  |  | 0
| FTG RESTEEL | 6390 | KG | 0.014 | 89.46 | 0.52 | 3322.8 | 0.52 | 3322.8 | 0.46 | 2939.4 | 9585 |  |  | 0
| FTG CONCRETE | 80 | M3 | 0.52 | 41.6 | 15.5 | 1240 | 0.54 | 43.2 | 65.8 | 5264 | 6547.2 |  |  | 0
| COMPACT BACKFILL | 35 | M2 | 0.92 | 32.2 | 9.64 | 337.4 | 0.32 | 11.2 |  | 0 | 348.6 |  |  | 0
TOTAL THIS SHEET |  |  |  |  | 202.26 |  | 6113.88 |  | 3399.56 |  | 8550.24 | 18063.68 |  |  | 0
JAN | 2008
A
B
C
OTHER

## CE-8
CONSTRUCTION COST ESTIMATE WORKSHEET |  |  |  | DATE PREPARED |  | SHEET 1 OF 1
2008-01-31
PROJECT: | WAREHOUSE BUILDING
LOCATION: | FORT HUNTSVILLE, AL
PLAN No. |  | ESTIMATOR: | J. SMITH |  | CHECKED BY: | J. DOE
SITE WORK
QUANTITY TAKE-OFF CALCULATIONS SHOULD BE
PREPARED IN A MANNER THAT IS CONSISTENT
WITH THE DISTRICT'S ESTABLISHED
PROCEDURES
JAN | 2008

## TQ
TELEPHONE QUOTATION SHEET | [5 empty] | CSI NUMBER: | BI 02.03
FIRM QUOTING: | STRONG STEEL |  |  | SOLICITATION NO: | DACW 97-01-R-0001
ADDRESS: |  |  |  |  | PROJECT: | PUMP PLANT
CITY: | ANY TOWN | STATE: | ZIP CODE:
COUNTY: | USA |  |  |  | LOCATION: | RM13, SPRUCE RIVER
PHONE: | (503) 326-3864
PERSON QUOTING: | JOE JONES |  |  |  | ESTIMATOR: | J. SMITH
DATE: | 2005-09-23 | TOTAL QUANTITY QUOTED: |  | 7.4 MT @ $1560/MT |  | AMOUNT: | 11544
ITEM QUOTED DESCRIPTION:
FURNISH & INSTALL ALL RESTEEL
INSTALLED:
INCLUDE SALES TAX:
PER PLANS/SPECIFICATIONS:
EXPLAIN EXCEPTIONS:
EXCEPT USING #4 BAR ILO #3 EXCLUDES SCAFFOLD & HOOK SERVICE
FREIGHT INCLUDED TO:
|  |  | TOTAL QUOTATION |  | 11544
WEIGHT |  |  | EXPORT PACKING
VOLUME |  |  | US INLAND FREIGHT
QUOTE VALID FOR | 30 DAYS |  | TOTAL MATERIAL COST
REMARKS:
YES
YES
YES
NO
NO
NO
FOB FACTORY
OTHER
FOB JOB
FAS PORT

## WR
WAGE RATE CALCULATIONS | [9 empty] | EFFECTIVE PERIOD
OCT 07 - SEP 08
PROJECT: | CONSTRUCT PUMP PLANT | [8 empty] | OPERATIONAL SHIFTS
1/10-5 DAY WEEK
LOCATION: | [5 empty] | ESTIMATOR |  |  |  | CHECKED BY
RT. BANK, RM 13, SPRUCE RIVER | [5 empty] | J. SMITH |  |  |  | J. DOE
LABOR COST
CRAFT DESCRIPTION |  | BASIC HOURLY WAGE RATE | OVERTIME |  | SUBTOTAL (b+d) | TAXES & INS |  | SUBTOTAL (e+g) | FRINGE BENEFITS | TRAVEL OR SUBSIST | TOTAL HOURLY COST (h+i+j)
|  |  | % OF (b) | AMT |  | % OF e | AMT
a |  | b | c | d | e | f | g | h | i | j | k
X-CARPENTER Foreman |  | 20.49 | 10 | 2.049 | 22.539 | 38.7 | 8.7226 | 31.2616 | 5.55 | 2 | 38.8116
X-CARPENTER |  | 18.49 | 10 | 1.849 | 20.339 | 38.7 | 7.8712 | 28.2102 | 5.55 | 2 | 35.7602
X-LABOR Foreman |  | 16.47 | 10 | 1.647 | 18.117 | 38.7 | 7.0113 | 25.1283 | 4.43 | 3 | 32.5583
X-LABOR |  | 14.47 | 10 | 1.447 | 15.917 | 38.7 | 6.1599 | 22.0769 | 4.43 | 3 | 29.5069 | USE "ANY STATE" DAVIS BACON WAGER AGREEMENT #AS970004 ADM #2 2/20/97 ***
X-EQOPRMED |  | 18.97 | 10 | 1.897 | 20.867 | 29.7 | 6.1975 | 27.0645 | 6.08 | 5 | 38.1445 | 50 HR WORK WEEK (5 - 10'S) - O.T. = 10% (PER O.T. TABLE)
X-EQOPOIL |  | 14.8 | 10 | 1.48 | 16.28 | 29.7 | 4.8352 | 21.1152 | 6.08 | 5 | 32.1952
X-CEMTFINR |  | 17.91 | 10 | 1.791 | 19.701 | 29.7 | 5.8512 | 25.5522 | 5.08 | 3 | 33.6322 | USE FOREMAN PREMIUM = |  | 2 | /HR
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 | FICA & FED UNEMPLOYMENT |  | 7.7%
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 | STATE UNEMPLOYMENT |  | 3%
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 | WORKMAN COMP
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 |  | CARPENTER | 28%
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 |  | LABOR | 28%
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 |  | OPERATOR | 19%
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 |  | CEMENT FINISHER | 19%
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  | AMT d: 0; AMT e: 0; AMT h: 0; AMT k: 0 | *** LOCAL PREVAILING WAGES ARE LESS THAN DAVIS BACON WAGES
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0 |  |  | 0
JAN | 2008

## CPR
CREW AND PRODUCTIVITY REPORT | [5 empty] | DATE PREPARED
2008-01-31
PROJECT: |  |  |  | PREPARED BY |  |  | CREW REF NO.
WAREHOUSE BUILDING |  |  |  | J. SMITH |  |  | B-25
LOCATION: |  |  |  | CHECKED BY
FORT HUNTSVILLE, AL |  |  |  | J. DOE
CREW COMPOSITION
WORK TYPE |  | WORK SCHEDULE |  |  | SPECIAL INFORMATION
PLACE CONCRETE |  | 1-10 HR; 5 DAYS/WEEK
CREW DESCRIPTION |  |  | NO. REQUIRED IN CREW |  | LABOR COST |  | EQUIPMENT COST
|  |  | M | E | HOURLY* RATE ($/HR) | TOTAL FOR CREW ($/HR) | HOURLY RATE ($/HR) | TOTAL FOR CREW ($/HR)
HYD SPCRANE 30T C757200 |  |  |  | 1 |  | 0 | 42.61 | 42.61
CONC BKT, 2 CY, 83071055 |  |  |  | 1 |  | 0 | 0.56 | 0.56 | EQUIP RATES HAVE BEEN ADJ FOR 50 HR WORK WEEK
CONC VIB, 2 X " A. C65XX00 |  |  |  | 1 |  | 0 | 0.35 | 0.35 | AND RATES TAKEN FROM EP 1110-1-8, VOL 3.
AIR COMP, 250 CFM. A2070480 |  |  |  | 1 |  | 0 | 8.66 | 8.66 | LABOR RATES TAKEN FROM DAVIS BACON AGREEMENT
AIR HOSE 1 K X 100'. A2070480 |  |  |  | 2 |  | 0 | 0.56 | 1.12 | GENERAL DECISION NUMBER
X-EAOPR MED |  |  | 1 |  | 38.15 | 38.15 |  | 0
X-LABOR Foreman |  |  | 1 |  | 32.56 | 32.56 |  | 0
X-LABOR |  |  | 4 |  | 29.51 | 118.04 |  | 0
X-CEMTFNR |  |  | 1 |  | 33.63 | 33.63 |  | 0
[6 empty] | 0 |  | 0
TOTAL |  | HOURS | 7 | 6 | LABOR COST | 222.38 | EQUIPMENT COST | 53.3
CREW PRODUCTIVITY
WORK TASK |  | PRODUCTIVITY RATE (UNIT/HR) | LABOR |  | EQUIPMENT $/UNIT | COMMENTS
|  |  | MH/UNIT | $/UNIT
PLACE CONCRETE |  | 75 M3/HR | 0.93 | 29.65 | 7.17
*INCLUDING FRINGE BENEFITS
JAN | 2008